## Sheet1
Company Name | Team Name | January Planned | January Time Spent | January Difference | February Planned | February Time Spent | February Difference | March Planned | March Time Spent | March Difference | April Planned | April Time Spent | April Difference | May Planned | May Time Spent | May Difference | June Planned | June Time Spent | June Difference | Total planned (up to this sprint) | Total Planned - Yearly | Total Time Spent - Yearly | Total Difference - Yearly
CPB - P-295 GCP Migration | Algo | 2.5 | 0 | 2.5 | 2.5 | 0 | 2.5 | 2.5 | 0 | 2.5 | 2.5 | 0 | 2.5 | 2.5 | 0 | 2.5 | 2.5 | 0 | 2.5 | 15 | 30 | 15 | 15
| Bi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dev | 10 | 0 | 10 | 10 | 0 | 10 | 10 | 0 | 10 | 10 | 0 | 10 | 10 | 0 | 10 | 10 | 0 | 10 | 60 | 120 | 60 | 60
| Devops | 3.33 | 0 | 3.33 | 3.33 | 0 | 3.33 | 3.33 | 0 | 3.33 | 3.33 | 0 | 3.33 | 3.33 | 0 | 3.33 | 3.33 | 0 | 3.33 | 20 | 40 | 20 | 20
| System Architect | 4.17 | 0 | 4.17 | 4.17 | 0 | 4.17 | 4.17 | 0 | 4.17 | 4.17 | 0 | 4.17 | 4.17 | 0 | 4.17 | 4.17 | 0 | 4.17 | 25 | 50 | 25 | 25
CPB 279 PROJECTS | Algo | 8.75 | 0 | 8.75 | 8.75 | 10.38 | -1.62 | 8.75 | 28.7 | -19.95 | 8.75 | 12 | -3.25 | 8.75 | 3.88 | 4.88 | 8.75 | 9 | -0.25 | -11.45 | 105 | -11.45 | 116.45
| Bi | 2.67 | 0.5 | 2.17 | 2.67 | 12 | -9.33 | 2.67 | 13.5 | -10.83 | 2.67 | 0 | 2.67 | 2.67 | 0 | 2.67 | 2.67 | 4.99 | -2.32 | -14.99 | 32 | -14.99 | 46.99
| Dev | 7.92 | 15.12 | -7.21 | 7.92 | 19 | -11.08 | 7.92 | 22 | -14.08 | 7.92 | 0 | 7.92 | 7.92 | 0 | 7.92 | 7.92 | 3 | 4.92 | -11.62 | 95 | -11.62 | 106.62
| Devops | 11.17 | 3 | 8.17 | 11.17 | 6 | 5.17 | 11.17 | 4 | 7.17 | 11.17 | 1.5 | 9.67 | 11.17 | 0 | 11.17 | 11.17 | 1.56 | 9.6 | 50.94 | 134 | 50.94 | 83.06
| System Architect | 6.42 | 0 | 6.42 | 6.42 | 0 | 6.42 | 6.42 | 0 | 6.42 | 6.42 | 0 | 6.42 | 6.42 | 0 | 6.42 | 6.42 | 0 | 6.42 | 38.5 | 77 | 38.5 | 38.5
CPB- P-296 Server rooms | Algo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Devops | 2.08 | 0 | 2.08 | 2.08 | 0 | 2.08 | 2.08 | 0 | 2.08 | 2.08 | 0 | 2.08 | 2.08 | 0 | 2.08 | 2.08 | 0 | 2.08 | 12.5 | 25 | 12.5 | 12.5
| System Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPB-271 UPKEEP | Algo | 1.75 | 2.5 | -0.75 | 1.75 | 9 | -7.25 | 1.75 | 3 | -1.25 | 1.75 | 8.5 | -6.75 | 1.75 | 18 | -16.25 | 1.75 | 19 | -17.25 | -49.5 | 21 | -49.5 | 70.5
| Bi | 2.92 | 11.12 | -8.21 | 2.92 | 18.5 | -15.58 | 2.92 | 1.75 | 1.16 | 2.92 | 12.75 | -9.83 | 2.92 | 10 | -7.08 | 2.92 | 28.01 | -25.1 | -64.64 | 35 | -64.64 | 99.64
| Dev | 15.83 | 10.25 | 5.58 | 15.83 | 25.5 | -9.67 | 15.83 | 18.5 | -2.67 | 15.83 | 35.5 | -19.67 | 15.83 | 31 | -15.17 | 15.83 | 30 | -14.17 | -55.75 | 190 | -55.75 | 245.75
| Devops | 34.25 | 30.8 | 3.45 | 34.25 | 0 | 34.25 | 34.25 | 23.6 | 10.65 | 34.25 | 23.6 | 10.65 | 34.25 | 0 | 34.25 | 34.25 | 15.58 | 18.68 | 111.92 | 411 | 111.92 | 299.08
| System Architect | 4.5 | 0 | 4.5 | 4.5 | 0 | 4.5 | 4.5 | 0 | 4.5 | 4.5 | 0 | 4.5 | 4.5 | 0 | 4.5 | 4.5 | 0 | 4.5 | 27 | 54 | 27 | 27

## January
Custom field (Budget) | Issue id | Issue_key | Company Name | Team Name | Assignee | Time Spent (Days) | Sprint | Date | Month
P271 - CPB Upkeep Computational (CPB) | 60853 | MIC-1103 | CPB-271 UPKEEP | Algo | robertoo |  | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 66973 | INTBIOM-209 | CPB-271 UPKEEP | Algo | anatm | 2.5 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 62901 | MIC-1126 | CPB-271 UPKEEP | Bi | michala | 1.625 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 60704 | MIC-1096 | CPB-271 UPKEEP | Bi | michala | 5 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 66972 | INTBIOM-208 | CPB-271 UPKEEP | Bi | liorr | 4.5 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 62817 | MIC-1123 | CPB-271 UPKEEP | Dev | duduz | 0.25 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 60859 | MIC-1108 | CPB-271 UPKEEP | Dev | hodayam | 0 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 62403 | INTBIOM-129 | CPB-271 UPKEEP | Dev | duduz | 0.25 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 62302 | INTBIOM-127 | CPB-271 UPKEEP | Dev | duduz | 0.5 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 63304 | CPB-1161 | CPB-271 UPKEEP | Dev | nerias | 1 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 63205 | CPB-1152 | CPB-271 UPKEEP | Dev | duduz | 3.25 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 60820 | CPB-1132 | CPB-271 UPKEEP | Dev | noama | 5 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 66956 | CPB-1442 | CPB-271 UPKEEP | Devops | morank | 30.8 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 61001 | CPB-1141 | CPB 279 PROJECTS | Bi | liorr | 0.5 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 62404 | CPB-1144 | CPB 279 PROJECTS | Dev | duduz | 0.125 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 62003 | CPB-1142 | CPB 279 PROJECTS | Dev | hodayam | 0.625 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 60910 | CPB-1139 | CPB 279 PROJECTS | Dev | noama | 5 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 60842 | CPB-1134 | CPB 279 PROJECTS | Dev | hodayam | 6.625 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 60821 | CPB-1133 | CPB 279 PROJECTS | Dev | nerias | 2.75 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 66957 | CPB-1443 | CPB 279 PROJECTS | Devops | morank | 3 | Jan 2024 | 2024-01-01 | 1

## February
Custom field (Budget) | Issue id | Issue_key | Company Name | Team Name | Assignee | Time Spent (Days) | Sprint | Date | Month
P271 - CPB Upkeep Computational (CPB) | 63502 | MIC-1138 | CPB-271 UPKEEP | Algo | anatm | 1 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63303 | CPB-1160 | CPB-271 UPKEEP | Algo | itair | 8 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 65202 | MIC-1153 | CPB-271 UPKEEP | Bi | michala | 3 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64001 | MIC-1140 | CPB-271 UPKEEP | Bi | michala | 5 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 62600 | MIC-1117 | CPB-271 UPKEEP | Bi | Iliaz |  | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 65204 | CPB-1201 | CPB-271 UPKEEP | Bi | liorr | 3.5 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63605 | CPB-1172 | CPB-271 UPKEEP | Bi | liorr | 4 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63602 | CPB-1169 | CPB-271 UPKEEP | Bi | iliab | 3 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64801 | INTBIOM-154 | CPB-271 UPKEEP | Dev | noama | 0.125 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64700 | CPB-1186 | CPB-271 UPKEEP | Dev | nerias | 2 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64404 | CPB-1182 | CPB-271 UPKEEP | Dev | nerias | 3 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64403 | CPB-1181 | CPB-271 UPKEEP | Dev | nerias | 3 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64402 | CPB-1180 | CPB-271 UPKEEP | Dev | nerias | 2 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63802 | CPB-1175 | CPB-271 UPKEEP | Dev | noama | 1.375 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63617 | CPB-1174 | CPB-271 UPKEEP | Dev | duduz | 3.25 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63309 | CPB-1166 | CPB-271 UPKEEP | Dev | nerias | 1 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63308 | CPB-1165 | CPB-271 UPKEEP | Dev | nerias | 3 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63307 | CPB-1164 | CPB-271 UPKEEP | Dev | nerias | 2 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63306 | CPB-1163 | CPB-271 UPKEEP | Dev | nerias | 1 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63305 | CPB-1162 | CPB-271 UPKEEP | Dev | nerias | 1 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 62500 | CPB-1145 | CPB-271 UPKEEP | Dev | noama | 2.75 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63211 | CPB-1158 | CPB 279 PROJECTS | Algo | itair | 3 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63207 | CPB-1154 | CPB 279 PROJECTS | Algo | robertoo | 4.375 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63206 | CPB-1153 | CPB 279 PROJECTS | Algo | robertoo | 3 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 64501 | CPB-1184 | CPB 279 PROJECTS | Bi | liorr | 4 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 64200 | CPB-1177 | CPB 279 PROJECTS | Bi | liorr | 5 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63604 | CPB-1171 | CPB 279 PROJECTS | Bi | iliab | 3 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 65500 | CPB-1235 | CPB 279 PROJECTS | Dev | nerias | 2 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 64503 | CPB-1185 | CPB 279 PROJECTS | Dev | hodayam | 4.875 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63900 | CPB-1176 | CPB 279 PROJECTS | Dev | noama | 4 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63204 | CPB-1151 | CPB 279 PROJECTS | Dev | hodayam | 2.875 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63202 | CPB-1149 | CPB 279 PROJECTS | Dev | hodayam | 4.875 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 62202 | CPB-1143 | CPB 279 PROJECTS | Dev | hodayam | 0.375 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 66959 | DEVOPS-569 | CPB 279 PROJECTS | Devops | morank | 6 | Feb-2024 | 2024-02-01 | 2

## March
Custom field (Budget) | Issue id | Issue_key | Company Name | Team Name | Assignee | Time Spent (Days) | Sprint | Date | Month
P271 - CPB Upkeep Computational (CPB) | 66529 | GEN-128 | CPB-271 UPKEEP | Algo | itair | 1.25 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66332 | CPB-1296 | CPB-271 UPKEEP | Algo | robertoo |  | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66324 | CPB-1288 | CPB-271 UPKEEP | Algo | robertoo | 1 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66011 | CPB-1243 | CPB-271 UPKEEP | Algo | itair | 0.75 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66547 | MIC-1204 | CPB-271 UPKEEP | Bi | iliab | 0.875 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66524 | MIC-1202 | CPB-271 UPKEEP | Bi | liorr | 0.75 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65207 | CPB-1204 | CPB-271 UPKEEP | Bi | iliab | 0.125 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65206 | CPB-1203 | CPB-271 UPKEEP | Bi | gala | 0.0020833 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66479 | CPB-1330 | CPB-271 UPKEEP | Dev | duduz | 2 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66234 | CPB-1247 | CPB-271 UPKEEP | Dev | nerias | 0.375 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65800 | CPB-1242 | CPB-271 UPKEEP | Dev | noama | 1.125 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65319 | CPB-1230 | CPB-271 UPKEEP | Dev | noama | 1 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65318 | CPB-1229 | CPB-271 UPKEEP | Dev | nerias | 2 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65317 | CPB-1228 | CPB-271 UPKEEP | Dev | noama | 2 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65316 | CPB-1227 | CPB-271 UPKEEP | Dev | noama | 1 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65313 | CPB-1224 | CPB-271 UPKEEP | Dev | hodayam | 1.5 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65309 | CPB-1220 | CPB-271 UPKEEP | Dev | nerias | 2 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65306 | CPB-1217 | CPB-271 UPKEEP | Dev | hodayam | 5 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65205 | CPB-1202 | CPB-271 UPKEEP | Dev | duduz | 0.5 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66203 | DEVOPS-475 | CPB-271 UPKEEP | Devops | morank | 0.125 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66100 | DEVOPS-473 | CPB-271 UPKEEP | Devops | morank | 0.5 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65801 | DEVOPS-471 | CPB-271 UPKEEP | Devops | vladz |  | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65606 | DEVOPS-467 | CPB-271 UPKEEP | Devops | morank | 0.125 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65503 | DEVOPS-465 | CPB-271 UPKEEP | Devops | morank |  | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65502 | DEVOPS-464 | CPB-271 UPKEEP | Devops | morank | 22.85 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 66415 | CPB-1320 | CPB 279 PROJECTS | Algo | robertoo | 3 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 66227 | CPB-1246 | CPB 279 PROJECTS | Algo | itair | 1.2 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65615 | CPB-1240 | CPB 279 PROJECTS | Algo | robertoo | 2.25 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65614 | CPB-1239 | CPB 279 PROJECTS | Algo | robertoo | 2 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65214 | CPB-1211 | CPB 279 PROJECTS | Algo | itair | 10.25 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 63212 | CPB-1159 | CPB 279 PROJECTS | Algo | itair | 3.5 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 63210 | CPB-1157 | CPB 279 PROJECTS | Algo | robertoo | 0.5 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 63209 | CPB-1156 | CPB 279 PROJECTS | Algo | itair | 4 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 63208 | CPB-1155 | CPB 279 PROJECTS | Algo | robertoo | 2 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 66666 | CPB-1376 | CPB 279 PROJECTS | Bi | michala | 2 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 66657 | CPB-1372 | CPB 279 PROJECTS | Bi | liorr | 1 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65508 | CPB-1237 | CPB 279 PROJECTS | Bi | liorr | 3 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65024 | CPB-1197 | CPB 279 PROJECTS | Bi | liorr | 0.5 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65022 | CPB-1195 | CPB 279 PROJECTS | Bi | liorr | 4 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65021 | CPB-1194 | CPB 279 PROJECTS | Bi | liorr | 1 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65020 | CPB-1193 | CPB 279 PROJECTS | Bi | liorr | 1 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65017 | CPB-1190 | CPB 279 PROJECTS | Bi | iliab | 1 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 66268 | CPB-1266 | CPB 279 PROJECTS | Dev | nerias | 4 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65701 | CPB-1241 | CPB 279 PROJECTS | Dev | nerias | 2.5 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65315 | CPB-1226 | CPB 279 PROJECTS | Dev | noama | 1.75 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65314 | CPB-1225 | CPB 279 PROJECTS | Dev | noama | 1.75 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65311 | CPB-1222 | CPB 279 PROJECTS | Dev | hodayam | 1.875 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65310 | CPB-1221 | CPB 279 PROJECTS | Dev | nerias | 1.625 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65308 | CPB-1219 | CPB 279 PROJECTS | Dev | nerias | 2 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65307 | CPB-1218 | CPB 279 PROJECTS | Dev | hodayam | 2.875 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65301 | CPB-1216 | CPB 279 PROJECTS | Dev | hodayam | 2.625 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65300 | CPB-1215 | CPB 279 PROJECTS | Dev | hodayam | 1 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 66924 | CPB-1430 | CPB 279 PROJECTS | Devops | vladz | 4 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 63203 | CPB-1150 | CPB 279 PROJECTS | Devops | vladz |  | Mar-2024 | 2024-03-01 | 3

## April
Custom field (Budget) | Issue id | Issue_key | Company Name | Team Name | Assignee | Time Spent (Days) | Sprint | Date | Month
P271 - CPB Upkeep Computational (CPB) | 66333 | CPB-1297 | CPB-271 UPKEEP | Algo | itair | 2.5 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66328 | CPB-1292 | CPB-271 UPKEEP | Algo | robertoo | 4 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66311 | CPB-1275 | CPB-271 UPKEEP | Algo | itair | 2 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66561 | MIC-1207 | CPB-271 UPKEEP | Bi | iliab | 5.75 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66444 | MIC-1180 | CPB-271 UPKEEP | Bi | michala | 1 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66427 | MIC-1172 | CPB-271 UPKEEP | Bi | liorr | 3 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66660 | CPB-1373 | CPB-271 UPKEEP | Bi | michala | 3 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66624 | MIC-1215 | CPB-271 UPKEEP | Dev | duduz | 0.5 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66426 | MIC-1171 | CPB-271 UPKEEP | Dev | duduz | 1 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66640 | LBI-154 | CPB-271 UPKEEP | Dev | duduz | 0.5 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66569 | INTBIOM-177 | CPB-271 UPKEEP | Dev | duduz | 0.25 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66575 | CPB-1368 | CPB-271 UPKEEP | Dev | nerias | 0.125 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66495 | CPB-1350 | CPB-271 UPKEEP | Dev | duduz | 1 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66487 | CPB-1342 | CPB-271 UPKEEP | Dev | noama | 2 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66490 | CPB-1341 | CPB-271 UPKEEP | Dev | duduz | 3 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66488 | CPB-1339 | CPB-271 UPKEEP | Dev | noama | 6.125 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66486 | CPB-1338 | CPB-271 UPKEEP | Dev | duduz | 2 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66494 | CPB-1337 | CPB-271 UPKEEP | Dev | noama | 4.375 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66485 | CPB-1336 | CPB-271 UPKEEP | Dev | hodayam | 5.75 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66509 | CPB-1335 | CPB-271 UPKEEP | Dev | hodayam | 1 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66508 | CPB-1334 | CPB-271 UPKEEP | Dev | hodayam | 1 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66416 | CPB-1321 | CPB-271 UPKEEP | Dev | hodayam | 1.5 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 65504 | CPB-1236 | CPB-271 UPKEEP | Dev | hodayam | 1.875 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 65320 | CPB-1231 | CPB-271 UPKEEP | Dev | nerias | 1.75 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 65312 | CPB-1223 | CPB-271 UPKEEP | Dev | nerias | 1.75 | Apr-2024 | 2024-04-01 | 4
P271 - CPB Upkeep Computational (CPB) | 66927 | CPB-1432 | CPB-271 UPKEEP | Devops | morank | 23.6 | Apr-2024 | 2024-04-01 | 4
P279 - CPB projects Computational (CPB) | 66619 | CPB-1369 | CPB 279 PROJECTS | Algo | itair | 2.375 | Apr-2024 | 2024-04-01 | 4
P279 - CPB projects Computational (CPB) | 66558 | CPB-1366 | CPB 279 PROJECTS | Algo | itair | 2 | Apr-2024 | 2024-04-01 | 4
P279 - CPB projects Computational (CPB) | 65217 | CPB-1214 | CPB 279 PROJECTS | Algo | itair | 3.125 | Apr-2024 | 2024-04-01 | 4
P279 - CPB projects Computational (CPB) | 65216 | CPB-1213 | CPB 279 PROJECTS | Algo | itair | 2 | Apr-2024 | 2024-04-01 | 4
P279 - CPB projects Computational (CPB) | 65215 | CPB-1212 | CPB 279 PROJECTS | Algo | itair | 2.5 | Apr-2024 | 2024-04-01 | 4
P279 - CPB projects Computational (CPB) | 66928 | CPB-1433 | CPB 279 PROJECTS | Devops | morank | 1.5 | Apr-2024 | 2024-04-01 | 4

## May
Custom field (Budget) | Issue id | Issue_key | Company Name | Team Name | Assignee | Time Spent (Days) | Sprint | Date | Month
P271 - CPB Upkeep Computational (CPB) | 66700 | MIC-1219 | CPB-271 UPKEEP | Algo | itair | 1 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66777 | CPB-1388 | CPB-271 UPKEEP | Algo | robertoo | 3.5 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66707 | CPB-1381 | CPB-271 UPKEEP | Algo | robertoo |  | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66405 | CPB-1319 | CPB-271 UPKEEP | Algo | itair | 3 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66336 | CPB-1300 | CPB-271 UPKEEP | Algo | itair | 2 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66326 | CPB-1290 | CPB-271 UPKEEP | Algo | robertoo | 2.5 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66325 | CPB-1289 | CPB-271 UPKEEP | Algo | itair | 3 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66312 | CPB-1276 | CPB-271 UPKEEP | Algo | itair | 3 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66778 | MIC-1225 | CPB-271 UPKEEP | Bi | gala | 0.5 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66849 | CPB-1395 | CPB-271 UPKEEP | Bi | liorr | 2.5 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66755 | CPB-1385 | CPB-271 UPKEEP | Bi | gala | 0.5 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66754 | CPB-1384 | CPB-271 UPKEEP | Bi | liorr | 3 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66661 | CPB-1374 | CPB-271 UPKEEP | Bi | liorr | 3.5 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66670 | MIC-1217 | CPB-271 UPKEEP | Dev | duduz | 0.0625 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66748 | LBI-163 | CPB-271 UPKEEP | Dev | hodayam | 1 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66703 | LBI-159 | CPB-271 UPKEEP | Dev | duduz | 0.125 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66842 | CPB-1393 | CPB-271 UPKEEP | Dev | hodayam | 0.625 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66836 | CPB-1391 | CPB-271 UPKEEP | Dev | duduz | 2 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66698 | CPB-1379 | CPB-271 UPKEEP | Dev | duduz | 2.5 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66662 | CPB-1375 | CPB-271 UPKEEP | Dev | duduz | 1 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66502 | CPB-1355 | CPB-271 UPKEEP | Dev | noama | 1 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66503 | CPB-1353 | CPB-271 UPKEEP | Dev | noama | 2.625 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66499 | CPB-1352 | CPB-271 UPKEEP | Dev | noama | 1.375 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66493 | CPB-1351 | CPB-271 UPKEEP | Dev | noama | 2 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66492 | CPB-1349 | CPB-271 UPKEEP | Dev | hodayam | 5 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66491 | CPB-1344 | CPB-271 UPKEEP | Dev | noama | 2.75 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66489 | CPB-1340 | CPB-271 UPKEEP | Dev | noama | 0.9375 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66507 | CPB-1333 | CPB-271 UPKEEP | Dev | noama | 1 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66506 | CPB-1332 | CPB-271 UPKEEP | Dev | noama | 2.5 | May-2024 | 2024-05-01 | 5
P271 - CPB Upkeep Computational (CPB) | 66346 | CPB-1310 | CPB-271 UPKEEP | Dev | duduz | 4.5 | May-2024 | 2024-05-01 | 5
P279 - CPB projects Computational (CPB) | 66734 | DEVOPS-527 | CPB 279 PROJECTS | Algo | robertoo | 0.125 | May-2024 | 2024-05-01 | 5
P279 - CPB projects Computational (CPB) | 66848 | CPB-1394 | CPB 279 PROJECTS | Algo | robertoo | 2.375 | May-2024 | 2024-05-01 | 5
P279 - CPB projects Computational (CPB) | 66687 | CPB-1378 | CPB 279 PROJECTS | Algo | itair | 1 | May-2024 | 2024-05-01 | 5
P279 - CPB projects Computational (CPB) | 66686 | CPB-1377 | CPB 279 PROJECTS | Algo | itair | 0.375 | May-2024 | 2024-05-01 | 5
P279 - CPB projects Computational (CPB) | 65023 | CPB-1196 | CPB 279 PROJECTS | Algo | itair |  | May-2024 | 2024-05-01 | 5

## June
Custom field (Budget) | Issue id | Issue_key | Company Name | Team Name | Assignee | Time Spent (Days) | Sprint | Date | Month
P271 - CPB Upkeep Computational (CPB) | 66881 | CPB-1410 | CPB-271 UPKEEP | Algo | itair | 3 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66880 | CPB-1409 | CPB-271 UPKEEP | Algo | itair | 3 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66449 | CPB-1325 | CPB-271 UPKEEP | Algo | itair | 1 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66338 | CPB-1302 | CPB-271 UPKEEP | Algo | itair | 5 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66337 | CPB-1301 | CPB-271 UPKEEP | Algo | itair | 3 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66334 | CPB-1298 | CPB-271 UPKEEP | Algo | itair | 3 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66313 | CPB-1277 | CPB-271 UPKEEP | Algo | robertoo | 1 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66593 | INTBIOM-180 | CPB-271 UPKEEP | Bi | liorr | 4 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 67077 | CPB-1484 | CPB-271 UPKEEP | Bi | gala | 3.5 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66940 | CPB-1438 | CPB-271 UPKEEP | Bi | iliab | 2.5 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66939 | CPB-1437 | CPB-271 UPKEEP | Bi | michala | 4.0125 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66938 | CPB-1436 | CPB-271 UPKEEP | Bi | liorr | 6.5 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66910 | CPB-1422 | CPB-271 UPKEEP | Bi | iliab | 2.5 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66835 | CPB-1390 | CPB-271 UPKEEP | Bi | liorr | 5 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 67070 | LBI-182 | CPB-271 UPKEEP | Dev | duduz |  | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66941 | LBI-174 | CPB-271 UPKEEP | Dev | duduz |  | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66878 | LBI-170 | CPB-271 UPKEEP | Dev | hodayam | 0.5 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 67014 | CPB-1450 | CPB-271 UPKEEP | Dev | noama | 1 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66837 | CPB-1392 | CPB-271 UPKEEP | Dev | duduz | 1 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66757 | CPB-1387 | CPB-271 UPKEEP | Dev | duduz | 2 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66652 | CPB-1371 | CPB-271 UPKEEP | Dev | noama | 4.625 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66501 | CPB-1354 | CPB-271 UPKEEP | Dev | duduz | 0.5 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66481 | CPB-1347 | CPB-271 UPKEEP | Dev | hodayam | 8.75 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66483 | CPB-1345 | CPB-271 UPKEEP | Dev | duduz | 2 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66482 | CPB-1343 | CPB-271 UPKEEP | Dev | hodayam | 7.625 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 66345 | CPB-1309 | CPB-271 UPKEEP | Dev | noama | 2 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 67115 | DEVOPS-594 | CPB-271 UPKEEP | Devops | morank | 14.7 | Jun-2024 | 2024-06-01 | 6
P271 - CPB Upkeep Computational (CPB) | 67045 | DEVOPS-576 | CPB-271 UPKEEP | Devops | morank | 0.875 | Jun-2024 | 2024-06-01 | 6
P279 - CPB projects Computational (CPB) | 66982 | CPB-1445 | CPB 279 PROJECTS | Algo | robertoo | 3 | Jun-2024 | 2024-06-01 | 6
P279 - CPB projects Computational (CPB) | 66876 | CPB-1408 | CPB 279 PROJECTS | Algo | robertoo | 1 | Jun-2024 | 2024-06-01 | 6
P279 - CPB projects Computational (CPB) | 66466 | CPB-1329 | CPB 279 PROJECTS | Algo | robertoo | 5 | Jun-2024 | 2024-06-01 | 6
P279 - CPB projects Computational (CPB) | 66860 | CPB-1406 | CPB 279 PROJECTS | Bi | iliab | 2 | Jun-2024 | 2024-06-01 | 6
P279 - CPB projects Computational (CPB) | 65019 | CPB-1192 | CPB 279 PROJECTS | Bi | michala | 2.9875 | Jun-2024 | 2024-06-01 | 6
P279 - CPB projects Computational (CPB) | 66811 | CPB-1389 | CPB 279 PROJECTS | Dev | duduz | 2 | Jun-2024 | 2024-06-01 | 6
P279 - CPB projects Computational (CPB) | 66484 | CPB-1348 | CPB 279 PROJECTS | Dev | duduz | 1 | Jun-2024 | 2024-06-01 | 6
P279 - CPB projects Computational (CPB) | 67059 | DEVOPS-577 | CPB 279 PROJECTS | Devops | vladz | 0.5625 | Jun-2024 | 2024-06-01 | 6
P279 - CPB projects Computational (CPB) | 66945 | DEVOPS-564 | CPB 279 PROJECTS | Devops | morank | 1 | Jun-2024 | 2024-06-01 | 6