## Sheet1
Company Name | Team Name | January Planned | January Time Spent | January Difference | February Planned | February Time Spent | February Difference | Total Planned | Total Time Spent | Total Difference | Total Planned - Yearly | Total Time Spent - Yearly | Total Difference - Yearly
AgPlenus | Algo | 3.33 | 4.88 | -1.54 | 3.33 | 1.44 | 1.9 | 6.67 | 6.31 | 0.35 | 40 | 6.31 | 33.69
| Bi | 1.17 | 0 | 1.17 | 1.17 | 0 | 1.17 | 2.33 | 0 | 2.33 | 14 | 0 | 14
| Dev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Biomica | Algo | 2.5 | 0 | 2.5 | 2.5 | 0 | 2.5 | 5 | 0 | 5 | 30 | 0 | 30
| Bi | 17.5 | 16.75 | 0.75 | 17.5 | 7.5 | 10 | 35 | 24.25 | 10.75 | 210 | 24.25 | 185.75
| Dev | 5.92 | 0 | 5.92 | 5.92 | 0 | 5.92 | 11.83 | 0 | 11.83 | 71 | 0 | 71
CPB | Algo | 10.5 | 0 | 10.5 | 10.5 | 19.88 | -9.38 | 21 | 19.88 | 1.12 | 126 | 19.88 | 106.12
| Bi | 5.58 | 10 | -4.42 | 5.58 | 27.5 | -21.92 | 11.17 | 37.5 | -26.33 | 67 | 37.5 | 29.5
| Dev | 42.17 | 25.38 | 16.79 | 42.17 | 42.13 | 0.04 | 84.33 | 67.5 | 16.83 | 506 | 67.5 | 438.5
Canonic | Algo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Casterra | Algo | 7.08 | 0 | 7.08 | 7.08 | 0 | 7.08 | 14.17 | 0 | 14.17 | 85 | 0 | 85
| Bi | 24.42 | 0 | 24.42 | 24.42 | 0 | 24.42 | 48.83 | 0 | 48.83 | 293 | 0 | 293
| Dev | 12.08 | 0 | 12.08 | 12.08 | 0 | 12.08 | 24.17 | 0 | 24.17 | 145 | 0 | 145
Chempass | Algo | 21.17 | 21.5 | -0.33 | 21.17 | 12.38 | 8.79 | 42.33 | 33.88 | 8.46 | 254 | 33.88 | 220.12
| Bi | 2.17 | 22.63 | -20.46 | 2.17 | 19 | -16.83 | 4.33 | 41.63 | -37.3 | 26 | 41.63 | -15.63
| Dev | 14.92 | 2.94 | 11.98 | 14.92 | 2.62 | 12.29 | 29.83 | 5.56 | 24.27 | 179 | 5.56 | 173.44
Colors | Algo | 1.67 | 3 | -1.33 | 1.67 | 1 | 0.67 | 3.33 | 4 | -0.67 | 20 | 4 | 16
| Bi | 3.08 | 10.5 | -7.42 | 3.08 | 6.5 | -3.42 | 6.17 | 17 | -10.83 | 37 | 17 | 20
| Dev | 0.83 | 0 | 0.83 | 0.83 | 0 | 0.83 | 1.67 | 0 | 1.67 | 10 | 0 | 10
Corp4clima | Algo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bi | 0.5 | 0 | 0.5 | 0.5 | 0 | 0.5 | 1 | 0 | 1 | 6 | 0 | 6
| Dev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Generator | Algo | 2.08 | 0 | 2.08 | 2.08 | 0 | 2.08 | 4.17 | 0 | 4.17 | 25 | 0 | 25
| Bi | 5.42 | 0 | 5.42 | 5.42 | 0 | 5.42 | 10.83 | 0 | 10.83 | 65 | 0 | 65
| Dev | 5 | 0 | 5 | 5 | 0 | 5 | 10 | 0 | 10 | 60 | 0 | 60
LavieBio | Algo | 2.92 | 0 | 2.92 | 2.92 | 3 | -0.08 | 5.83 | 3 | 2.83 | 35 | 3 | 32
| Bi | 5.25 | 23.12 | -17.88 | 5.25 | 4 | 1.25 | 10.5 | 27.12 | -16.62 | 63 | 27.12 | 35.88
| Dev | 4 | 6.88 | -2.88 | 4 | 0 | 4 | 8 | 6.88 | 1.12 | 48 | 6.88 | 41.12
MicroBoost | Algo | 2.5 | 0 | 2.5 | 2.5 | 5 | -2.5 | 5 | 5 | 0 | 30 | 5 | 25
| Bi | 8.5 | 3.5 | 5 | 8.5 | 6 | 2.5 | 17 | 9.5 | 7.5 | 102 | 9.5 | 92.5
| Dev | 2.92 | 2.25 | 0.67 | 2.92 | 7.12 | -4.21 | 5.83 | 9.38 | -3.54 | 35 | 9.38 | 25.62
PRoduct | Algo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dev | 0 | 0 | 0 | 0 | 1 | -1 | 0 | 1 | -1 | 0 | 1 | -1
The Kitchen | Algo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bi | 2.5 | 0 | 2.5 | 2.5 | 0 | 2.5 | 5 | 0 | 5 | 30 | 0 | 30
| Dev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-1 | Algo | 0 | 7 | -7 | 0 | 7 | -7 | 0 | 14 | -14 | 0 | 14 | -14
| Bi | 0 | 7.25 | -7.25 | 0 | 0 | 0 | 0 | 7.25 | -7.25 | 0 | 7.25 | -7.25
| Dev | 0 | 5.75 | -5.75 | 0 | 4.5 | -4.5 | 0 | 10.25 | -10.25 | 0 | 10.25 | -10.25
| Devops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AgPlenus | Devops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Biomica | Devops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CPB | Devops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Casterra | Devops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chempass | Devops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Colors | Devops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LavieBio | Devops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MicroBoost | Devops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PRoduct | Devops | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## January
Custom field (Budget) | Issue id | Issue_key | Company Name | Team Name | Assignee | Time Spent (Days) | Sprint | Date | Month
P145-Corteva - IA (Lavie) | 61901 | LBI-88 | LavieBio | Bi | iliab | 3 | Jan 2024 | 2024-01-01 | 1
P145-Corteva - IA (Lavie) | 60588 | LBI-61 | LavieBio | Bi | liorr | 2 | Jan 2024 | 2024-01-01 | 1
P192 - LAV 321 (Lavie) | 62813 | MIC-1120 | LavieBio | Dev | nerias | 1.125 | Jan 2024 | 2024-01-01 | 1
P210 - Herbicides Corteva (AgPlenus) | 60807 | AGPI-26 | AgPlenus | Algo | robertoo | 3.5 | Jan 2024 | 2024-01-01 | 1
P23 - Herbicides (AgPlenus) | 61801 | AGPI-29 | AgPlenus | Algo | robertoo | 0.125 | Jan 2024 | 2024-01-01 | 1
P23 - Herbicides (AgPlenus) | 61404 | AGPI-28 | AgPlenus | Dev | duduz |  | Jan 2024 | 2024-01-01 | 1
P24 - Fungicides (AgPlenus) | 62203 | AGPI-30 | AgPlenus | Algo | robertoo | 1.25 | Jan 2024 | 2024-01-01 | 1
P24 - Fungicides (AgPlenus) | 60827 | AGPI-27 | AgPlenus | Algo | anatm |  | Jan 2024 | 2024-01-01 | 1
P24 - Fungicides (AgPlenus) | 60572 | AGPI-20 | AgPlenus | Algo | anatm |  | Jan 2024 | 2024-01-01 | 1
P252 - Cancer Immun adjuvant (Biomica) | 62402 | INTBIOM-128 | Biomica | Bi | michala | 2 | Jan 2024 | 2024-01-01 | 1
P252 - Cancer Immun adjuvant (Biomica) | 60599 | INTBIOM-104 | Biomica | Bi | liorr | 4 | Jan 2024 | 2024-01-01 | 1
P252 - Cancer Immun adjuvant (Biomica) | 58304 | INTBIOM-59 | Biomica | Bi | iliab | 3.25 | Jan 2024 | 2024-01-01 | 1
P252 - Cancer Immun adjuvant (Biomica) | 58302 | INTBIOM-57 | Biomica | Bi | iliab | 2.5 | Jan 2024 | 2024-01-01 | 1
P255 - IBD (Biomica 2023) | 63301 | INTBIOM-134 | Biomica | Bi | liorr | 2 | Jan 2024 | 2024-01-01 | 1
P255 - IBD (Biomica 2023) | 62101 | INTBIOM-125 | Biomica | Bi | gala | 1.5 | Jan 2024 | 2024-01-01 | 1
P255 - IBD (Biomica 2023) | 62100 | INTBIOM-124 | Biomica | Bi | michala | 1.5 | Jan 2024 | 2024-01-01 | 1
P255 - IBD (Biomica 2023) | 57926 | INTBIOM-47 | Biomica | Dev | duduz |  | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 63316 | CHEM-900 | Chempass | Algo | itair | 3 | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 62400 | CHEM-888 | Chempass | Algo | robertoo | 1.75 | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 60863 | CHEM-878 | Chempass | Algo | robertoo | 1.025 | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 60816 | CHEM-871 | Chempass | Algo | anatm | 8 | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 60713 | CHEM-867 | Chempass | Algo | robertoo | 0.25 | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 62701 | CHEM-894 | Chempass | Bi | markb | 2.75 | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 61501 | CHEM-887 | Chempass | Bi | markb | 0.625 | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 60907 | CHEM-879 | Chempass | Bi | iliab | 1.5 | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 60627 | CHEM-857 | Chempass | Bi | markb | 5 | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 60626 | CHEM-856 | Chempass | Bi | markb | 12.7562 | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 62603 | CHEM-892 | Chempass | Dev | duduz | 0.25 | Jan 2024 | 2024-01-01 | 1
P264 - Product-CP (Chempass) | 62406 | CHEM-890 | Chempass | Dev | hodayam | 0.1875 | Dec 2023 | 2023-12-01 | 1
P264 - Product-CP (Chempass) | 61302 | CHEM-885 | Chempass | Dev | hodayam | 0.5 | Jan 2024 | 2024-01-01 | 1
P265 - Product- MB (Microboost) | 62502 | MIC-1116 | MicroBoost | Bi | iliab | 1 | Jan 2024 | 2024-01-01 | 1
P265 - Product- MB (Microboost) | 60689 | MIC-1089 | MicroBoost | Bi | gala | 2.5 | Jan 2024 | 2024-01-01 | 1
P265 - Product- MB (Microboost) | 60857 | MIC-1106 | MicroBoost | Dev | hodayam |  | Jan 2024 | 2024-01-01 | 1
P265 - Product- MB (Microboost) | 60690 | MIC-1090 | MicroBoost | Dev | duduz |  | Jan 2024 | 2024-01-01 | 1
P265 - Product- MB (Microboost) | 60681 | MIC-1087 | MicroBoost | Dev | nerias | 1.25 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 60853 | MIC-1103 | CPB | Algo | robertoo |  | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 62901 | MIC-1126 | CPB | Bi | michala | 3.5 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 60704 | MIC-1096 | CPB | Bi | michala | 5 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 62817 | MIC-1123 | CPB | Dev | duduz | 0.25 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 60859 | MIC-1108 | CPB | Dev | hodayam | 0 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 62403 | INTBIOM-129 | CPB | Dev | duduz | 0.25 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 62302 | INTBIOM-127 | CPB | Dev | duduz | 0.5 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 63304 | CPB-1161 | CPB | Dev | nerias | 1 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 63205 | CPB-1152 | CPB | Dev | duduz | 3 | Jan 2024 | 2024-01-01 | 1
P271 - CPB Upkeep Computational (CPB) | 60820 | CPB-1132 | CPB | Dev | noama | 5 | Jan 2024 | 2024-01-01 | 1
P273 - Product- Upkeep MB | 62601 | MIC-1118 | MicroBoost | Dev | duduz | 1 | Jan 2024 | 2024-01-01 | 1
P274 - Product- Upkeep ChemPass | 62818 | CHEM-897 | Chempass | Algo | robertoo |  | Jan 2024 | 2024-01-01 | 1
P274 - Product- Upkeep ChemPass | 62815 | CHEM-896 | Chempass | Algo | robertoo | 3.1 | Jan 2024 | 2024-01-01 | 1
P274 - Product- Upkeep ChemPass | 62405 | CHEM-889 | Chempass | Algo | robertoo | 0.375 | Jan 2024 | 2024-01-01 | 1
P274 - Product- Upkeep ChemPass | 60818 | CHEM-873 | Chempass | Algo | robertoo |  | Jan 2024 | 2024-01-01 | 1
P274 - Product- Upkeep ChemPass | 60817 | CHEM-872 | Chempass | Algo | robertoo | 3.5 | Jan 2024 | 2024-01-01 | 1
P274 - Product- Upkeep ChemPass | 60411 | CHEM-836 | Chempass | Algo | robertoo | 0.5 | Jan 2024 | 2024-01-01 | 1
P274 - Product- Upkeep ChemPass | 62604 | CHEM-893 | Chempass | Dev | noama | 1 | Jan 2024 | 2024-01-01 | 1
P274 - Product- Upkeep ChemPass | 60630 | CHEM-858 | Chempass | Dev | duduz | 1 | Jan 2024 | 2024-01-01 | 1
P274 - Product- Upkeep ChemPass | 60591 | CHEM-851 | Chempass | Dev | duduz |  | Jan 2024 | 2024-01-01 | 1
P274 - Product- Upkeep ChemPass | 60590 | CHEM-850 | Chempass | Dev | duduz |  | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 61001 | CPB-1141 | CPB | Bi | liorr | 1.5 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 62404 | CPB-1144 | CPB | Dev | duduz | 0.125 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 62003 | CPB-1142 | CPB | Dev | hodayam | 0.625 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 60910 | CPB-1139 | CPB | Dev | noama | 5 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 60842 | CPB-1134 | CPB | Dev | hodayam | 6.625 | Jan 2024 | 2024-01-01 | 1
P279 - CPB projects Computational (CPB) | 60821 | CPB-1133 | CPB | Dev | nerias | 3 | Jan 2024 | 2024-01-01 | 1
P290 - Colors (Product) | 61204 | COL-35 | Colors | Algo | anatm | 3 | Jan 2024 | 2024-01-01 | 1
P290 - Colors (Product) | 62606 | COL-37 | Colors | Bi | gala | 1 | Jan 2024 | 2024-01-01 | 1
P290 - Colors (Product) | 62300 | COL-36 | Colors | Bi | gala | 0.5 | Jan 2024 | 2024-01-01 | 1
P290 - Colors (Product) | 61203 | COL-34 | Colors | Bi | gala | 3 | Jan 2024 | 2024-01-01 | 1
P290 - Colors (Product) | 61002 | COL-32 | Colors | Bi | michala | 3 | Jan 2024 | 2024-01-01 | 1
P290 - Colors (Product) | 60642 | COL-27 | Colors | Bi | michala | 3 | Jan 2024 | 2024-01-01 | 1
P82 - ICL (Lavie) | 62806 | LBI-96 | LavieBio | Bi | iliab | 2 | Jan 2024 | 2024-01-01 | 1
P82 - ICL (Lavie) | 62805 | LBI-95 | LavieBio | Bi | liorr | 5 | Jan 2024 | 2024-01-01 | 1
P82 - ICL (Lavie) | 60908 | LBI-86 | LavieBio | Bi | iliab | 2 | Jan 2024 | 2024-01-01 | 1
P82 - ICL (Lavie) | 60618 | LBI-65 | LavieBio | Bi | liorr | 5 | Jan 2024 | 2024-01-01 | 1
P82 - ICL (Lavie) | 60617 | LBI-64 | LavieBio | Bi | iliab | 2 | Jan 2024 | 2024-01-01 | 1
P86 -Product ( Lavie) | 62605 | LBI-94 | LavieBio | Bi | markb | 0.25 | Jan 2024 | 2024-01-01 | 1
P86 -Product ( Lavie) | 61500 | LBI-87 | LavieBio | Bi | markb | 1.875 | Jan 2024 | 2024-01-01 | 1
P86 -Product ( Lavie) | 62303 | LBI-93 | LavieBio | Dev | duduz | 1 | Jan 2024 | 2024-01-01 | 1
P86 -Product ( Lavie) | 60900 | LBI-85 | LavieBio | Dev | hodayam | 4.75 | Jan 2024 | 2024-01-01 | 1
P86 -Product ( Lavie) | 60839 | LBI-82 | LavieBio | Dev | duduz |  | Jan 2024 | 2024-01-01 | 1
P86 -Product ( Lavie) | 60829 | LBI-74 | LavieBio | Dev | duduz |  | Jan 2024 | 2024-01-01 | 1
P999 - General (LavieBio) | 60694 | INTBIOM-113 | -1 | Algo | robertoo |  | Jan 2024 | 2024-01-01 | 1
P999 - General (LavieBio) | 60840 | LBI-83 | -1 | Bi | iliab | 3.25 | Jan 2024 | 2024-01-01 | 1
P999 - General (LavieBio) | 60901 | LBI-84 | -1 | Dev | hodayam | 5.5 | Jan 2024 | 2024-01-01 | 1
P999 – General (Biomica) | 62809 | INTBIOM-131 | -1 | Algo | anatm | 7 | Jan 2024 | 2024-01-01 | 1
P999 – General (Biomica) | 62703 | INTBIOM-130 | -1 | Bi | michala | 2 | Jan 2024 | 2024-01-01 | 1
P999 – General (Biomica) | 61700 | INTBIOM-120 | -1 | Bi | michala | 2 | Jan 2024 | 2024-01-01 | 1
P999 – General (Biomica) | 65303 | INTBIOM-159 | -1 | Dev | noama | 0.25 | Nov 2023 | 2023-11-01 | 1
P999 – General (Biomica) | 60848 | INTBIOM-118 | -1 | Dev | nerias |  | Jan 2024 | 2024-01-01 | 1
P999 – General (Biomica) | 60722 | INTBIOM-115 | -1 | Dev | duduz |  | Jan 2024 | 2024-01-01 | 1

## February
Custom field (Budget) | Issue id | Issue_key | Company Name | Team Name | Assignee | Time Spent (Days) | Sprint | Date | Month
P23 - Herbicides (AgPlenus) | 65506 | AGPI-45 | AgPlenus | Algo | robertoo | 0.0625 | Feb-2024 | 2024-02-01 | 2
P23 - Herbicides (AgPlenus) | 65404 | AGPI-41 | AgPlenus | Algo | robertoo | 0.0625 | Feb-2024 | 2024-02-01 | 2
P23 - Herbicides (AgPlenus) | 65000 | AGPI-38 | AgPlenus | Algo | robertoo |  | Feb-2024 | 2024-02-01 | 2
P23 - Herbicides (AgPlenus) | 64601 | AGPI-37 | AgPlenus | Algo | robertoo | 0.125 | Feb-2024 | 2024-02-01 | 2
P23 - Herbicides (AgPlenus) | 64400 | AGPI-36 | AgPlenus | Algo | robertoo | 0.1875 | Feb-2024 | 2024-02-01 | 2
P24 - Fungicides (AgPlenus) | 63100 | AGPI-33 | AgPlenus | Algo | anatm | 1.0002 | Feb-2024 | 2024-02-01 | 2
P252 - Cancer Immun adjuvant (Biomica) | 63614 | INTBIOM-140 | Biomica | Bi | liorr | 1 | Feb-2024 | 2024-02-01 | 2
P252 - Cancer Immun adjuvant (Biomica) | 63500 | INTBIOM-137 | Biomica | Bi | iliab | 2 | Feb-2024 | 2024-02-01 | 2
P252 - Cancer Immun adjuvant (Biomica) | 63310 | INTBIOM-136 | Biomica | Bi | michala | 1 | Feb-2024 | 2024-02-01 | 2
P252 - Cancer Immun adjuvant (Biomica) | 61206 | INTBIOM-119 | Biomica | Bi | michala | 1 | Feb-2024 | 2024-02-01 | 2
P252 - Cancer Immun adjuvant (Biomica) | 60200 | INTBIOM-96 | Biomica | Bi | michala | 1.5 | Feb-2024 | 2024-02-01 | 2
P255 - IBD (Biomica 2023) | 63302 | INTBIOM-135 | Biomica | Bi | liorr | 1 | Feb-2024 | 2024-02-01 | 2
P264 - Product-CP (Chempass) | 63403 | CHEM-905 | Chempass | Algo | robertoo | 5 | Feb-2024 | 2024-02-01 | 2
P264 - Product-CP (Chempass) | 63002 | CHEM-898 | Chempass | Algo | anatm | 7 | Feb-2024 | 2024-02-01 | 2
P264 - Product-CP (Chempass) | 63628 | CHEM-908 | Chempass | Bi | markb | 0.875 | Feb-2024 | 2024-02-01 | 2
P264 - Product-CP (Chempass) | 63612 | CHEM-907 | Chempass | Bi | markb | 6.375 | Feb-2024 | 2024-02-01 | 2
P264 - Product-CP (Chempass) | 62811 | CHEM-895 | Chempass | Bi | markb | 11.75 | Feb-2024 | 2024-02-01 | 2
P264 - Product-CP (Chempass) | 65007 | CHEM-913 | Chempass | Dev | hodayam | 0.625 | Feb-2024 | 2024-02-01 | 2
P264 - Product-CP (Chempass) | 63400 | CHEM-903 | Chempass | Dev | hodayam | 1 | Feb-2024 | 2024-02-01 | 2
P265 - Product- MB (Microboost) | 63010 | MIC-1136 | MicroBoost | Algo | itair | 3 | Feb-2024 | 2024-02-01 | 2
P265 - Product- MB (Microboost) | 63011 | MIC-1137 | MicroBoost | Bi | gala |  | Feb-2024 | 2024-02-01 | 2
P265 - Product- MB (Microboost) | 62910 | MIC-1132 | MicroBoost | Bi | iliab | 2 | Feb-2024 | 2024-02-01 | 2
P265 - Product- MB (Microboost) | 62908 | MIC-1131 | MicroBoost | Bi | iliab | 3 | Feb-2024 | 2024-02-01 | 2
P265 - Product- MB (Microboost) | 62913 | MIC-1135 | MicroBoost | Dev | duduz | 2 | Feb-2024 | 2024-02-01 | 2
P265 - Product- MB (Microboost) | 62906 | MIC-1129 | MicroBoost | Dev | noama | 2.5 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63502 | MIC-1138 | CPB | Algo | anatm | 1 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63303 | CPB-1160 | CPB | Algo | itair | 8 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 65202 | MIC-1153 | CPB | Bi | michala | 3 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64001 | MIC-1140 | CPB | Bi | michala | 5 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 62600 | MIC-1117 | CPB | Bi | Iliaz |  | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 65204 | CPB-1201 | CPB | Bi | liorr | 0.5 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63605 | CPB-1172 | CPB | Bi | liorr | 4 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63602 | CPB-1169 | CPB | Bi | iliab | 3 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64801 | INTBIOM-154 | CPB | Dev | noama | 0.125 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64700 | CPB-1186 | CPB | Dev | nerias | 2 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64404 | CPB-1182 | CPB | Dev | nerias | 3 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64403 | CPB-1181 | CPB | Dev | nerias | 3 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 64402 | CPB-1180 | CPB | Dev | nerias | 2 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63802 | CPB-1175 | CPB | Dev | noama | 1.375 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63617 | CPB-1174 | CPB | Dev | duduz | 3.2521 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63309 | CPB-1166 | CPB | Dev | nerias | 1 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63308 | CPB-1165 | CPB | Dev | nerias | 3 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63307 | CPB-1164 | CPB | Dev | nerias | 2 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63306 | CPB-1163 | CPB | Dev | nerias | 1 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 63305 | CPB-1162 | CPB | Dev | nerias | 1 | Feb-2024 | 2024-02-01 | 2
P271 - CPB Upkeep Computational (CPB) | 62500 | CPB-1145 | CPB | Dev | noama | 2.75 | Feb-2024 | 2024-02-01 | 2
P273 - Product- Upkeep MB | 60100 | MIC-1043 | MicroBoost | Algo | itair | 2 | Feb-2024 | 2024-02-01 | 2
P273 - Product- Upkeep MB | 63806 | MIC-1139 | MicroBoost | Bi | liorr | 0.5 | Feb-2024 | 2024-02-01 | 2
P273 - Product- Upkeep MB | 62816 | MIC-1122 | MicroBoost | Bi | liorr | 0.5 | Feb-2024 | 2024-02-01 | 2
P273 - Product- Upkeep MB | 64804 | MIC-1143 | MicroBoost | Dev | hodayam | 1 | Feb-2024 | 2024-02-01 | 2
P273 - Product- Upkeep MB | 62814 | MIC-1121 | MicroBoost | Dev | noama | 1.625 | Feb-2024 | 2024-02-01 | 2
P274 - Product- Upkeep ChemPass | 64109 | CHEM-911 | Chempass | Algo | robertoo | 0.375 | Feb-2024 | 2024-02-01 | 2
P274 - Product- Upkeep ChemPass | 65324 | CHEM-918 | Chempass | Dev | noama | 1 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63211 | CPB-1158 | CPB | Algo | itair | 3 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63207 | CPB-1154 | CPB | Algo | robertoo | 4.375 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63206 | CPB-1153 | CPB | Algo | robertoo | 3.5 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 64501 | CPB-1184 | CPB | Bi | liorr | 4 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 64200 | CPB-1177 | CPB | Bi | liorr | 5 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63604 | CPB-1171 | CPB | Bi | iliab | 3 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 65500 | CPB-1235 | CPB | Dev | nerias | 2 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 64503 | CPB-1185 | CPB | Dev | hodayam | 4.875 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63900 | CPB-1176 | CPB | Dev | noama | 2 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63204 | CPB-1151 | CPB | Dev | hodayam | 2.875 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 63202 | CPB-1149 | CPB | Dev | hodayam | 4.875 | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 62202 | CPB-1143 | CPB | Dev | hodayam |  | Feb-2024 | 2024-02-01 | 2
P279 - CPB projects Computational (CPB) | 64201 | CPB-1178 | CPB | Devops | morank |  | Feb-2024 | 2024-02-01 | 2
P282 - Product general (Product 2023) | 59700 | GEN-102 | PRoduct | Dev | duduz | 1 | Feb-2024 | 2024-02-01 | 2
P290 - Colors (Product) | 65603 | COL-43 | Colors | Algo | anatm | 1 | Feb-2024 | 2024-02-01 | 2
P290 - Colors (Product) | 65305 | COL-41 | Colors | Bi | gala | 0.5 | Feb-2024 | 2024-02-01 | 2
P290 - Colors (Product) | 65200 | COL-40 | Colors | Bi | michala | 2 | Feb-2024 | 2024-02-01 | 2
P290 - Colors (Product) | 63609 | COL-39 | Colors | Bi | michala | 2 | Feb-2024 | 2024-02-01 | 2
P290 - Colors (Product) | 63608 | COL-38 | Colors | Bi | gala | 2 | Feb-2024 | 2024-02-01 | 2
P82 - ICL (Lavie) | 62905 | LBI-99 | LavieBio | Bi | gala | 2.5 | Feb-2024 | 2024-02-01 | 2
P85 -Syngenta (Lavie) | 64303 | LBI-108 | LavieBio | Algo | anatm | 3 | Feb-2024 | 2024-02-01 | 2
P85 -Syngenta (Lavie) | 63607 | LBI-104 | LavieBio | Bi | gala | 1.5 | Feb-2024 | 2024-02-01 | 2
P999 - General (LavieBio) | 63404 | LBI-102 | -1 | Dev | noama | 3 | Feb-2024 | 2024-02-01 | 2
P999 – General (Biomica) | 63616 | INTBIOM-143 | -1 | Algo | anatm | 2 | Feb-2024 | 2024-02-01 | 2
P999 – General (Biomica) | 62810 | INTBIOM-132 | -1 | Algo | anatm | 5 | Feb-2024 | 2024-02-01 | 2
P999 – General (Biomica) | 64508 | INTBIOM-149 | -1 | Dev | duduz | 1.5 | Feb-2024 | 2024-02-01 | 2

## March
Custom field (Budget) | Issue id | Issue_key | Company Name | Team Name | Assignee | Time Spent (Days) | Sprint | Date | Month
P216 - Core collection & Data base (Canonic) | 65607 | CAN-178 | Canonic | Bi | gala | 1.25 | Mar-2024 | 2024-03-01 | 3
P24 - Fungicides (AgPlenus) | 63007 | AGPI-32 | AgPlenus | Algo | anatm | 1 | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 66537 | CHEM-970 | Chempass | Algo | anatm | 6 | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 66431 | CHEM-956 | Chempass | Algo | anatm | 3 | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 66211 | CHEM-942 | Chempass | Algo | robertoo | 2 | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 65600 | CHEM-923 | Chempass | Algo | itair |  | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 65220 | CHEM-915 | Chempass | Algo | anatm | 8 | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 65405 | CHEM-922 | Chempass | Bi | markb | 4.25 | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 65323 | CHEM-917 | Chempass | Bi | markb | 4 | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 65322 | CHEM-916 | Chempass | Bi | markb | 9.0167 | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 63501 | CHEM-906 | Chempass | Bi | markb |  | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 63317 | CHEM-901 | Chempass | Bi | markb | 1.7521 | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 66212 | CHEM-943 | Chempass | Dev | duduz | 0.125 | Mar-2024 | 2024-03-01 | 3
P264 - Product-CP (Chempass) | 65402 | CHEM-921 | Chempass | Dev | duduz | 0.25 | Mar-2024 | 2024-03-01 | 3
P265 - Product- MB (Microboost) | 64505 | MIC-1142 | MicroBoost | Bi | iliab | 7 | Mar-2024 | 2024-03-01 | 3
P265 - Product- MB (Microboost) | 65703 | DEVOPS-468 | MicroBoost | Devops | morank | 1 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66529 | GEN-128 | CPB | Algo | itair | 1.25 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66332 | CPB-1296 | CPB | Algo | robertoo |  | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66324 | CPB-1288 | CPB | Algo | robertoo | 1 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66011 | CPB-1243 | CPB | Algo | itair | 0.5 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66547 | MIC-1204 | CPB | Bi | iliab | 1 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66524 | MIC-1202 | CPB | Bi | liorr | 0.75 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65207 | CPB-1204 | CPB | Bi | iliab | 4 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65206 | CPB-1203 | CPB | Bi | gala | 4 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66479 | CPB-1330 | CPB | Dev | duduz | 2 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66234 | CPB-1247 | CPB | Dev | nerias | 0.375 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65800 | CPB-1242 | CPB | Dev | noama | 1.125 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65319 | CPB-1230 | CPB | Dev | noama | 1 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65318 | CPB-1229 | CPB | Dev | nerias | 2 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65317 | CPB-1228 | CPB | Dev | noama | 2 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65316 | CPB-1227 | CPB | Dev | noama | 1 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65313 | CPB-1224 | CPB | Dev | hodayam | 1.5 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65309 | CPB-1220 | CPB | Dev | nerias | 2 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65306 | CPB-1217 | CPB | Dev | hodayam | 5 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65205 | CPB-1202 | CPB | Dev | duduz | 0.5 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66203 | DEVOPS-475 | CPB | Devops | morank | 0.125 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 66100 | DEVOPS-473 | CPB | Devops | morank | 0.5 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65801 | DEVOPS-471 | CPB | Devops | vladz |  | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65606 | DEVOPS-467 | CPB | Devops | morank | 0.125 | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65503 | DEVOPS-465 | CPB | Devops | morank |  | Mar-2024 | 2024-03-01 | 3
P271 - CPB Upkeep Computational (CPB) | 65502 | DEVOPS-464 | CPB | Devops | morank |  | Mar-2024 | 2024-03-01 | 3
P273 - Product- Upkeep MB | 65102 | MIC-1147 | MicroBoost | Bi | michala | 3 | Mar-2024 | 2024-03-01 | 3
P274 - Product- Upkeep ChemPass | 66401 | CHEM-955 | Chempass | Algo | robertoo | 0.125 | Mar-2024 | 2024-03-01 | 3
P274 - Product- Upkeep ChemPass | 66473 | CHEM-968 | Chempass | Dev | noama | 0.375 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 66415 | CPB-1320 | CPB | Algo | robertoo | 1 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 66227 | CPB-1246 | CPB | Algo | itair |  | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65615 | CPB-1240 | CPB | Algo | robertoo | 4.25 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65614 | CPB-1239 | CPB | Algo | robertoo | 2 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65214 | CPB-1211 | CPB | Algo | itair | 10.25 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 63212 | CPB-1159 | CPB | Algo | itair | 3.5 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 63210 | CPB-1157 | CPB | Algo | robertoo | 0.5 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 63209 | CPB-1156 | CPB | Algo | itair | 4 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 63208 | CPB-1155 | CPB | Algo | robertoo | 2 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65508 | CPB-1237 | CPB | Bi | liorr | 4 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65024 | CPB-1197 | CPB | Bi | liorr | 0.5 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65022 | CPB-1195 | CPB | Bi | liorr | 2 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65021 | CPB-1194 | CPB | Bi | liorr | 1 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65020 | CPB-1193 | CPB | Bi | liorr | 2 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65017 | CPB-1190 | CPB | Bi | iliab | 1 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 66268 | CPB-1266 | CPB | Dev | nerias | 3.125 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65701 | CPB-1241 | CPB | Dev | nerias | 2.5 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65315 | CPB-1226 | CPB | Dev | noama | 1.75 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65314 | CPB-1225 | CPB | Dev | noama | 1.75 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65311 | CPB-1222 | CPB | Dev | hodayam | 1.875 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65310 | CPB-1221 | CPB | Dev | nerias | 1.625 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65308 | CPB-1219 | CPB | Dev | nerias | 2 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65307 | CPB-1218 | CPB | Dev | hodayam | 2.875 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65301 | CPB-1216 | CPB | Dev | hodayam | 2.625 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65300 | CPB-1215 | CPB | Dev | hodayam | 2 | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 65025 | CPB-1198 | CPB | Devops | morank |  | Mar-2024 | 2024-03-01 | 3
P279 - CPB projects Computational (CPB) | 63203 | CPB-1150 | CPB | Devops | vladz |  | Mar-2024 | 2024-03-01 | 3
P290 - Colors (Product) | 65601 | COL-42 | Colors | Bi | michala | 2 | Mar-2024 | 2024-03-01 | 3
P401 - The Kitchen | 66497 | KFF-8 | The Kitchen | Dev | duduz | 0.5 | Mar-2024 | 2024-03-01 | 3
P402 - Casterra Generator | 66232 | GEN-122 | Casterra | Bi | gala | 0.75 | Mar-2024 | 2024-03-01 | 3
P402 - Casterra Generator | 65212 | GEN-120 | Casterra | Bi | michala | 4 | Mar-2024 | 2024-03-01 | 3
P402 - Casterra Generator | 65211 | GEN-118 | Casterra | Bi | michala | 2 | Mar-2024 | 2024-03-01 | 3
P402 - Casterra Generator | 65210 | GEN-117 | Casterra | Bi | michala | 3 | Mar-2024 | 2024-03-01 | 3
P402 - Casterra Generator | 65209 | GEN-113 | Casterra | Bi | michala | 4 | Mar-2024 | 2024-03-01 | 3
P402 - Casterra Generator | 66498 | INTCAS-22 | Casterra | Dev | duduz | 0.25 | Mar-2024 | 2024-03-01 | 3
P402 - Casterra Generator | 66262 | GEN-121 | Casterra | Dev | duduz | 2 | Mar-2024 | 2024-03-01 | 3
P402 - Casterra Generator | 65400 | GEN-119 | Casterra | Dev | noama | 10.5 | Mar-2024 | 2024-03-01 | 3
P402 - Casterra Generator | 65401 | GEN-116 | Casterra | Dev | duduz | 1.5021 | Mar-2024 | 2024-03-01 | 3
P402 - Casterra Generator | 66202 | GEN-110 | Casterra | Dev | duduz | 0.5 | Mar-2024 | 2024-03-01 | 3
P403 - Run Generator (on going) - Casterra | 65509 | INTCAS-10 | Casterra | Bi | liorr | 1.5 | Mar-2024 | 2024-03-01 | 3
P82 - ICL (Lavie) | 65302 | LBI-115 | LavieBio | Dev | duduz | 0.5 | Mar-2024 | 2024-03-01 | 3
P85 -Syngenta (Lavie) | 66206 | LBI-119 | LavieBio | Algo | anatm |  | Mar-2024 | 2024-03-01 | 3
P85 -Syngenta (Lavie) | 66228 | LBI-129 | LavieBio | Bi | gala | 1 | Mar-2024 | 2024-03-01 | 3
P85 -Syngenta (Lavie) | 66217 | LBI-125 | LavieBio | Bi | liorr | 5 | Mar-2024 | 2024-03-01 | 3
P85 -Syngenta (Lavie) | 66216 | LBI-124 | LavieBio | Bi | liorr | 1.5 | Mar-2024 | 2024-03-01 | 3
P85 -Syngenta (Lavie) | 66215 | LBI-123 | LavieBio | Bi | iliab | 4 | Mar-2024 | 2024-03-01 | 3
P85 -Syngenta (Lavie) | 66214 | LBI-122 | LavieBio | Bi | michala | 3 | Mar-2024 | 2024-03-01 | 3
P85 -Syngenta (Lavie) | 66205 | LBI-118 | LavieBio | Bi | liorr | 1 | Mar-2024 | 2024-03-01 | 3
P85 -Syngenta (Lavie) | 66104 | LBI-117 | LavieBio | Bi | iliab | 4 | Mar-2024 | 2024-03-01 | 3
P85 -Syngenta (Lavie) | 65900 | LBI-116 | LavieBio | Bi | gala | 1.25 | Mar-2024 | 2024-03-01 | 3
P85 -Syngenta (Lavie) | 65014 | LBI-112 | LavieBio | Bi | gala | 1.5 | Mar-2024 | 2024-03-01 | 3
P85 -Syngenta (Lavie) | 62909 | LBI-100 | LavieBio | Bi | gala | 2.5 | Mar-2024 | 2024-03-01 | 3
P999 – General (Biomica) | 66530 | INTBIOM-172 | -1 | Algo | anatm | 1 | Mar-2024 | 2024-03-01 | 3
P999 – General (Biomica) | 66263 | INTBIOM-166 | -1 | Bi | liorr | 1.75 | Mar-2024 | 2024-03-01 | 3
P999 – General (Biomica) | 64900 | INTBIOM-156 | -1 | Dev | nerias | 2.875 | Mar-2024 | 2024-03-01 | 3